Initial Commissioning Tasks for the LTU/FEL Run (2008-2009)

Oct. 22, 2008 (frisch1)

The First Four Weeks (Nov. 3 - 28, 2008)

Main Goal:	Re-establish bright beam to 52-SL2 at 30 Hz & 0.25 nC

- All injector, linac, and BSY pre-beam checkout done and all magnets standardized to startup configs (per R. Iverson)

- No unnecessary new controls software released yet

- Check LLRF reference system timing

- Process L0A, L0B, TCAV1 to full power (as measured on SCP)

- Process RF Gun – stage 1.

  - Check LLRF hardware pulse width limit at low power.

  - Process gun based on SCP readout to 5 MV/M

  - Initial calibration of EPICS LLRF.

- Re-establish UV drive laser on VCC and cathode with 1.2-mm iris and ~20 µJ

  - Run through laser checklist

  - Re-GOLD (if necessary) and switch ON the laser pointing feedback loops

  - Manual Schottky scan watching YAG01

  - Set laser phase to 30 degrees.

  - Check laser phase feedback loop

- Process RF Gun – Stage 2

  - Beam to gun spectrometer

  - Adjust RF power for 5MV (do not exceed old SCP limit)

  - Calibrate LLRF signals for 5MV

  - Laser off

  - Process gun to 6MV

  - Laser on

  - Recalibrate on gun spectrometer.

  - Set peak RF trip threshold (frisch)

- Take beam to 6-MeV spectrometer (1-10 Hz)

  - Image cathode on YAG01 and verify cathode position (no “spider”)

  - Measure QE

  - Align laser using solenoid-scan GUI (with Aug. ’08 offsets)

  - Steer beam flat in x and y using minimal corrector tweaks

  - Calibrate gun RF amplitude on YAGG1 (6-MeV spectrometer)

  - Re-GOLD (if necessary) and switch ON the following feedback loops:

    - Laser loop

    - Laser Power Set

    - Bunch charge

- Take beam to 135-MeV spectrometer (1-10 Hz, see procedure)

  - New laser-heater chicane OFF, LH-undulator not installed, and no IR laser

  - Phase and calibrate L0a amplitude on YAGS2 (135-MeV spectrometer)

    - Note – set lattice and magnets for 64 MeV.

  - Phase and calibrate L0b amplitude on YAGS2 (135-MeV spectrometer)

  - Check YAGS2 for “on-crest” operation (no linear chirp)

  - Measure OTR2 Twiss & emittance and run β-matching, and correct any induced steering

  - Measure bunch length on OTR2 with TCAV0

  - Re-GOLD (if necessary) and switch ON injector feedback loops:

    - Gun launch

    - Injector launch

- Take beam to TD11 stopper with BC1 ON at R56 = 45.5 mm, BC1 offset = 247.6 mm, and energy = 250 MeV (1-10 Hz)

  - Adjust L1S voltage roughly to get beam through BC1 (L1X OFF)

  - Steer beam reasonably flat in x and y using minimal corrector tweaks

  - Calibrate L1S amplitude at crest phase using the BC1 BPM (L1X OFF)

  - Re-GOLD and switch ON BC1 energy feedback (with DL1 energy, but no BC1 bunch length yet)

  - Phase L1S OFF crest by 21 degrees (see OP GUI)

  - Calibrate L1X amplitude at decal-crest phase using the BC1 BPM (scan L1X voltage and correlate with L1S voltage feedback response needed to hold BC1 BPM constant in x)

  - Re-GOLD (with BPMS LI21 201 x = +0.1 mm) and switch ON X-cavity launch feedback loop

  - Phase L1X OFF crest by 160 degrees (see OP GUI)

  - Check BL11 mirror is inserted

  - If ready, re-GOLD (if necessary) and switch ON BC1-bunch-length feedback loop (+ DL1-energy + BC1-energy)

- Checkout injector BPM timing, attenuation, and reasonable response to a few oscillations (any BPMs now backwards or not responding in x, y, or TMIT?)

- Take beam to 52-SL2 stopper at 13.64 GeV with BC2 ON at R56 = 24.7 mm, BC2 offset = 363.0 mm, and BC2 energy = 4.3 GeV (1-10 Hz)

  - Standardize LI21 quadrupole and corrector magnets

  - Add or remove klystrons to get beam through BC2

  - Steer beam flat (or to config) in x and y using minimal corrector tweaks

  - Phase all RF stations (21-3 to 30-8, with all SBST PDES = 0)

  - Set L2 RF phase to 36 deg using phase-scan GUI

  - Check BL21 mirror is inserted

  - Re-GOLD (if necessary) and switch ON linac/energy feedback loops:

    - L2 launch

    - LI26 SCP loop

    - DL1-energy, BC1-energy, BC1-bunch-length, BC2-energy, and BC2-bunch-length

    - FB31 energy loop

- Measure and correct emittance at OTR2, WS12, and WS28

  - Follow standard injector emittance tuning procedure

  - Scan beam position in L1X for emittance

  - Orbit bumps for emittance at S28

- L2 phase scans / emittance measurements / bunch length measurements

- Software Releases

  - Start releasing all downtime software in order recommended by software group.

  - After each major release, beam back to PR55, measure full performance

- Turn on laser heater Bends

  - Re-match

  - Measure emittance

  - Retune emittance

- If laser heater and LTU not ready yet, other studies

  - Ultra-short bunch studies

  - Jitter studies

  - COTR studies

- Turn on laser heater

- Beam through LTU